MINISTRY OF EDUCATION AND TRAINING

VAN LANG UNIVERSITY

SCHOOL OF TECHNOLOGY

THE GATHERING PROJECT

d&c

Project Plan

A Realtime 2D Virtual Workspace Platform

Document version: 1.1

Document version: 1.0

# REVISION HISTORY

| Date | Version | Description | Authorize by |
| --- | --- | --- | --- |
| February 02 2026 | 1.0 | Create document | Le Tan Dat |
| February 3, 2025 February 7, 2025 | 1.1 | Update document format | Le Tan Dat |

TABLE 1: DOCUMENT REVISION HISTORY

# TABLE OF CONTENTS

REVISION HISTORY	1

TABLE OF CONTENTS	2

LIST OF FIGURES	3

LIST OF TABLES	4

I. OVERVIEW	5

1. PURPOSE, SCOPE, AND OBJECTIVES	5

2. PROJECT DELIVERABLES	7

3. PROJECT’S PROCESSES LIST	8

II. PROJECT RESOURCE PLAN	10

1. ROLE, RESPONSIBILITIES, AND AUTHORITY	10

2. MEMBERS	12

3. REQUIRED KNOWLEDGE & SKILL SET	13

4. TRAINING NEEDS	16

III. PROJECT SCHEDULE	18

1. PROJECT DEVELOPMENT METHODOLOGY	18

2. PROJECT DEVELOPMENT PHASES/ITERATION	22

IV. PROJECT RISK MANAGEMENT PLAN	30

1. RISK SOURCE AND CATEGORY	30

2. RISK MANAGEMENT APPROACH	31

3. TOOLS AND TECHNIQUE	32

4. RISK ITEM TO BE MANAGED	32

5. RISK MONITORING AND CONTROL	34

V. PROJECT STAKEHOLDERS INVOLVEMENT	35

VI. PROJECT COMMUNICATION PLAN	36

1. KEY CONTACTS LIST	36

2. COMMUNICATION METHODOLOGY	36

# LIST OF FIGURES

Figure 1: Processes List	8

FIGURE 2: PROCESSES RELATIONSHIP	9

FIGURE 3: INCREMENTAL MODEL	18

# LIST OF TABLES

TABLE 1: DOCUMENT REVISION HISTORY	1

Table 2: PROJECT DELIVERABLES	8

TABLE 3: PROJECT ROLES, RESPONSIBILITIES AND AUTHORITY	12

TABLE 4: TEAM MEMBER ROLES AND RESPONSIBILITIES	12

TABLE 5: REQUIRED KNOWLEDGE AND SKILLSET	15

TABLE 6: TRAINING NEEDS	16

TABLE 7: PROJECT DEVELOPMENT PHASES\ITERATION	22

TABLE 8: PROJECT DETAILED SCHEDULE	27

TABLE 9: LIST OF RISK SOURCE THAT ARE APPLICABLE TO THE PROJECT	29

TABLE 10: LIST OF RISK CATEGORY THAT ARE USED BY THE PROJECT FOR ORGANIZING RISKS	29

TABLE 11: RISK ITEMS TO BE MANAGED	32

TABLE 12: PROJECT STAKEHOLDER INVOLVEMENT	33

TABLE 13 PROJECT KEY CONTACTS LIST	34

TABLE 14 COMMUNICATION METHODOLOGY	34

# I. OVERVIEW

## 1. PURPOSE, SCOPE, AND OBJECTIVES

The purpose of this project is to design, develop, and deploy a web-based virtual workspace platform inspired by the Gather model, enabling users to interact in a 2D spatial environment using avatars with real-time multiplayer presence, distance-based audio/video communication, and persistent virtual spaces for work, meetings, and social collaboration.

This project will be conducted as a Capstone Project, requiring the team to apply software engineering knowledge, real-time system design principles, and project management best practices to deliver a functional and scalable product within a defined timeframe and resource constraint. The project emphasizes not only feature implementation but also architectural soundness, system reliability, and maintainability.

System Overview

The system is a virtual 2D workspace where users can enter persistent spaces (e.g., offices, classrooms, event areas), control avatars, and naturally interact with others based on spatial proximity. Core capabilities include:

- Realtime Multiplayer Environment

  - Live synchronization of avatar movement, presence, and interaction states among multiple concurrent users.

  - Low-latency state updates to ensure smooth navigation and consistent shared world perception.

- Spatial Audio/Video Communication

  - Automatic joining and leaving of voice/video conversations based on distance between avatars.

  - Dynamic audio attenuation and connection management to simulate real-world proximity interactions.

- Persistent Workspace and Space Management

  - Persistent virtual spaces that retain configuration, layout, and access permissions across sessions.

  - Administrative tools for creating, editing, and managing spaces, rooms, and user roles.

- Collaboration and Communication Features

  - Text chat (public and private).

  - Meeting modes for structured discussions and presentations.

  - Optional integration points for calendars or scheduling systems (within defined scope).

Project Deliverables

The final deliverables of the project include:

- Product Deliverables

  - A fully functional web application supporting 2D virtual spaces, avatar movement, real-time presence, and spatial audio/video communication.

  - An administrative interface for workspace and user management.

- Documentation Deliverables

  - Concept of Operations (ConOps).

  - Software Requirements Specification (SRS).

  - Software Architecture Specification and Design Documents.

  - Deployment and User Guides.

  - Project Development and Final Report.

Project Scope

The project scope is defined from both project management and software development perspectives, focusing on the following areas:

- Solution Analysis and Architecture Design

  - Research and design of a real-time, browser-based virtual workspace architecture, including frontend rendering, backend services, and media communication components.

- Development and Management Processes

  - Definition and application of a structured development methodology suitable for real-time and interactive systems.

  - Establishment of monitoring and control mechanisms for progress, quality, and risks.

- Requirements Engineering

  - Elicitation, specification, and validation of functional and non-functional requirements related to real-time interaction, scalability, and usability.

- Project Planning and Control

  - Effort estimation, scheduling, milestone definition, and continuous progress tracking throughout the project lifecycle.

- Process Definition and Measurement

  - Definition of development and quality assurance processes.

  - Measurement of progress, system performance, and deliverable completion against defined objectives.

- Software Development Lifecycle Execution

  - System design, implementation, integration, testing, and deployment of the virtual workspace platform.

- Knowledge Sharing and Team Enablement

  - Structured knowledge sharing within the development team to ensure consistent understanding of real-time systems, Web technologies, and communication protocols.

- Decision-Making and Trade-off Analysis

  - Evaluation of technical and architectural options, balancing performance, complexity, scalability, and development constraints to achieve an optimal solution.

## 2. PROJECT DELIVERABLES

| Deliverable | Description |
| --- | --- |
| Process Description | Documentation describing all development, management, and quality assurance processes applied throughout the project lifecycle. |
| Concept of Operation (ConsOp) | A document describing the proposed virtual workspace solution, including the real collaboration problems addressed, limitations of existing online communication tools, and the team’s proposed Gather-like approach. |
| Software Requirement Specification (SRS) | A document specifying functional and non-functional requirements of the virtual workspace system, including realtime interaction, spatial audio/video, scalability, and usability requirements. |
| Software Architecture Driver Specification (SAD) | A document identifying and analyzing key architectural drivers derived from the SRS, such as performance, latency, scalability, and reliability constraints. |
| Software Architecture Specification (SAS) | A document describing the overall system architecture of the virtual workspace platform, including frontend, backend, realtime services, and media communication components. |
| Software Design Specification (SDS) | A document detailing the internal design of system modules, data flows, interaction logic, and component-level responsibilities. |
| Project Plan | The formal project plan defining scope, schedule, resources, risks, and management approach for the virtual workspace project. |
| Project charter | The document that formally authorizes the project, defines objectives, stakeholders, and assigns responsibilities to the project team. |
| Software Product | A deployable web-based virtual workspace application supporting 2D environments, avatar movement, realtime presence, and spatial audio/video interaction. |
| User Guide & Installation Guide | Documentation guiding users and administrators on how to access, use, configure, and deploy the virtual workspace system. |
| Presentation Slide | Slides used for Capstone project reporting, system demonstration, and final defense presentation. |
| Measurement Plan (MP), Analysis Plan (AP), Measurement Report (MR). | A set of documents defining metrics, data collection, analysis methods, and measurement results related to system performance, reliability, and project progress. |
| Risk Management Plan (RMP), Risk Tracking and Report (RTR). | Documentation describing risk identification, assessment, mitigation strategies, and continuous risk tracking throughout the project. |
| Testing Suit | A complete testing package including Test Plan (STP), Test Cases (STCs), and Test Reports (STR) covering functional, integration, performance, and usability testing. (STCs) and Test Report (STR). |

Table 2: PROJECT DELIVERABLES

## 3. PROJECT’S PROCESSES LIST

Figure 1: Processes List

Within the virtual workspace project inspired by the Gather model, all project processes are systematically categorized into three main groups to ensure effective execution and structured project governance. This process framework supports real-time collaboration, robust technical development, and controlled project oversight throughout the project lifecycle:

- Teamwork Processes:
These processes focus on improving team coordination, communication, and productivity, enabling the development team to collaborate effectively while addressing the challenges of real-time and interactive systems.

- Software Development Processes:
Defined within the Software Development Lifecycle (SDLC), these processes follow a plan-driven approach with controlled iteration, ensuring that real-time multiplayer functionality, spatial audio/video communication, and persistent workspace features are developed in a structured and predictable manner.

- Management Processes:
These processes provide planning, monitoring, and control mechanisms to manage scope, schedule, quality, and risks, ensuring the virtual workspace project is executed effectively and aligned with defined objectives.

.

The following figure illustrates the overall relationship between these processes.

FIGURE 2: PROCESSES RELATIONSHIP

# II. PROJECT RESOURCE PLAN

## 1. ROLE, RESPONSIBILITIES, AND AUTHORITY

| Prefix | Role | Responsibilities | Deliverables Authority |
| --- | --- | --- | --- |
| MT | Mentor | - Provide academic and technical guidance to support the development team in identifying and resolving project issues independently. • Conduct periodic reviews and weekly progress meetings. • Facilitate access to academic resources, tools, and reference materials required for project execution. |  |
| PM | Project Manager | - Ensure project (tasks) delivered on time, within budget and meet customer requirements. - Coordinate Plan, Monitoring & Control the tractability of team activities. - Analysis & monitoring each task of each team member on quality & progress. - Ensure every meeting is effective & active. - Perform monitoring, measuring, analysis & control the project. - Make decisions & solve the issue of team to ensure the top optimal team productivity. - Collect the weekly individual reports and send them to Mentor. - Collect the weekly feedback and send to Team. | - Project Charter - Project Plan - ConOps - SAD - SRS |
| GD | UX/UI Designer | - Design intuitive and visually coherent user interfaces for the 2D virtual workspace. • Define user interaction flows for avatar movement, proximity interaction, and workspace navigation. • Create wireframes, interactive prototypes, and UI guidelines. • Conduct usability evaluations and refine designs based on feedback. | - UX/UI wireframe - Prototypes - UI Design Guidelines |
| SA | Software Architect | • Define overall system architecture for the virtual workspace platform. • Design realtime system flow, service boundaries, and data communication mechanisms. • Ensure scalability, security, performance, and maintainability of the system. • Define technical standards and architectural best practices.. | • Software Architecture Specification (SAS) • Software Architecture Drivers (SAD) • Software Design Specification (SDS) |
| FE | Frontend Developer | • Develop the web-based client for the 2D virtual workspace. • Implement avatar rendering, movement logic, and UI components. • Integrate realtime APIs and media services with the frontend. • Optimize rendering performance and user experience. | • Software Product (Web Client) |
| BE | Backend / Realtime Developer | • Develop backend services and realtime communication mechanisms. • Implement presence synchronization, proximity logic, and session management. • Design and maintain APIs supporting frontend and media services. | • Backend Services • Realtime APIs |
| AV | Audio/Video Engineer. | • Design and implement spatial audio/video communication mechanisms. • Integrate WebRTC or media services for proximity-based interaction. • Monitor media performance and connection stability. | • Audio/Video Communication Module. |
| T | Tester | • Define testing strategies for frontend, backend, realtime, and audio/video components. • Design and execute test cases across functional, integration, performance, and usability testing. • Track defects, verify fixes, and support acceptance testing. | - Test Plan - Test Cases. - Defects Report. |

TABLE 3: PROJECT ROLES, RESPONSIBILITIES AND AUTHORITY

## 2. MEMBERS

As defined, our team has the rotate and merger techniques. All team members will work in the same development role. Here are the member and their responsibilities roles:

| Prefix | Role | Name of member |
| --- | --- | --- |
| PM | Project Manager | Pham Nguyen Thien Loc |
| BA | Business Analyst | Pham Nguyen Thien Loc |
| GD | UX/UI Designer | Le Tan Dat |
| SA | Software Architect | Pham Nguyen Thien Loc, Le Tan Dat, Banh Van Tran Phat |
| FE | Frontend Developer | Pham Nguyen Thien Loc, Le Tan Dat, Banh Van Tran Phat |
| BE | Backend / Realtime Developer | Pham Nguyen Thien Loc, Le Tan Dat, Banh Van Tran Phat |
| AV | Audio/Video Engineer | Banh Van Tran Phat |
| QA | Tester / QA Engineer | Pham Nguyen Thien Loc |

TABLE 4: TEAM MEMBER ROLES AND RESPONSIBILITIES

## 3. REQUIRED KNOWLEDGE & SKILL SET

| Prefix | Role | Required Knowledge & Skill Set |
| --- | --- | --- |
| PM | Project Manager | - Strong understanding of Plan-Driven & Incremental methodologies for project execution. - Experience in software development lifecycle (SDLC) and team coordination. - Knowledge of risk management, conflict resolution, and stakeholder communication. - Ability to create and manage project documentation (ConOps, Risk Management Plan, Progress Reports). - Strong leadership, decision-making, and problem-solving skills. |
| BA | Business Analyst | - Ability to elicit, analyze, and manage stakeholder requirements for virtual collaboration systems. - Translate user needs into functional and non-functional requirements (realtime interaction, usability, scalability). - Collaborate closely with UX, Software Architect, QA, and PM to ensure requirement consistency. - Ability to model system behavior using UML diagrams (use case, sequence, activity). |
| GD | UX/UI Designer | - Strong understanding of UI/UX principles for 2D virtual environments and interactive systems. - Experience designing avatar interaction flows, spatial navigation, and workspace layouts. - Proficiency with design tools (Figma or equivalent) for wireframes and interactive prototypes. - Knowledge of usability testing and accessibility principles for web applications. - Ability to collaborate with frontend developers to ensure design feasibility. |
| SA | Software Architect | - Deep knowledge of software architecture patterns for distributed and real-time systems. - Experience designing client-server architectures, realtime services, and media pipelines. - Understanding of scalability, latency, security, and fault tolerance. - Ability to define architectural drivers and document architecture and design decisions. - Experience creating Software Architecture and Design Specifications. |
| FE | Frontend Developer | - Proficiency in modern frontend development (React, TypeScript, HTML, CSS). - Experience rendering interactive 2D environments and managing real-time UI updates. - Knowledge of state management for realtime applications. - Ability to integrate frontend with backend and realtime APIs. - Skills in debugging, performance optimization, and cross-browser compatibility. |
| BE | Backend / Realtime Developer | - Strong knowledge of backend development using Node.js or equivalent platforms. - Experience implementing realtime communication (WebSocket, signaling services). - Ability to design APIs supporting presence synchronization and session management. - Understanding of concurrency, scalability, and data consistency in realtime systems. |
| AV | Audio/Video Engineer | - Knowledge of audio/video communication concepts and WebRTC fundamentals. - Experience with signaling, media streams, and connection lifecycle management. - Understanding of proximity-based or spatial audio/video logic. - Ability to monitor and optimize media performance and connection stability. |
| QA | Tester / QA Engineer | - - Strong understanding of software testing methodologies for web and realtime systems. - Ability to design and execute functional, integration, performance, and usability tests. - Experience testing realtime behavior, synchronization, and media stability. - Knowledge of defect tracking and reporting processes. - Ability to produce clear test documentation (Test Plan, Test Cases, Test Reports). |

TABLE 5: REQUIRED KNOWLEDGE AND SKILLSET

## 4. TRAINING NEEDS

| Role | Required Training | Training Duration |
| --- | --- | --- |
| Project Manager | - Plan-driven development with controlled iteration for interactive systems. - Project scheduling, progress tracking, and risk monitoring using tools such as Jira or GitHub Projects. - Writing and maintaining core project documentation (Project Plan, ConOps, Progress Reports). | 1–2 weeks |
| UX/UI Designer | - Designing UI/UX for 2D virtual environments and avatar-based interaction. - Using Figma for wireframes, interactive prototypes, and workspace layouts. - Usability testing and accessibility considerations for web applications. - Collaboration workflows with frontend developers. | 2–4 weeks |
| Software Architect | - Architecture design for distributed and realtime web systems. - Designing service boundaries, data flow, and realtime communication patterns. - Documenting architectural decisions and design specifications. | 2–4 weeks |
| Frontend Developer | - Advanced React fundamentals for interactive and realtime applications. - Rendering 2D environments and handling realtime state updates. - Integrating frontend with backend and realtime APIs. - Debugging and performance optimization for browser-based applications.. | 3-4 weeks |
| Backend / Realtime Developer | - Backend development for realtime systems using Node.js or equivalent platforms. - Implementing WebSocket or similar realtime communication mechanisms. - Designing APIs for presence synchronization and session management. | 3–5 weeks |
| Audio/Video Engineer | - Fundamentals of WebRTC and media communication. - Implementing signaling, connection management, and media streams. - Understanding proximity-based or spatial audio/video behavior. - Monitoring and optimizing media performance. | 3–4 weeks |
| Tester / QA Engineer | - Testing strategies for web-based and realtime systems. - Designing and executing functional, integration, performance, and usability tests. - Testing realtime synchronization and audio/video stability. - Writing test documentation and defect reports. | 2–3 weeks |

TABLE 6: TRAINING NEEDS

# III. PROJECT SCHEDULE

## 1. PROJECT DEVELOPMENT METHODOLOGY

The virtual workspace project inspired by the Gather model adopts a Plan-Driven development methodology with controlled iteration, utilizing a structured and predictive approach to ensure comprehensive planning, detailed documentation, and disciplined execution. This methodology is selected to align with the project’s constraints, including a limited team size, fixed academic milestones, and the requirement to deliver a stable Minimum Viable Product (MVP) within the defined project timeline.

The Plan-Driven approach is implemented using the Incremental Model as the delivery strategy. Under this model, the system is developed and delivered through a series of well-defined functional increments, each increment being fully planned, implemented, tested, and reviewed before proceeding to the next. This approach is particularly suitable for a real-time and interactive system such as a virtual workspace platform.

FIGURE 3: INCREMENTAL MODEL

Why Plan-Driven?

The Plan-Driven methodology is well-suited for this virtual workspace project due to its ability to provide a predictable and controllable framework for managing the complexity of real-time multiplayer systems and spatial audio/video communication. Unlike purely adaptive methodologies, Plan-Driven emphasizes upfront analysis and architectural planning, which is critical for systems with strict performance and reliability requirements.

The key reasons for choosing the Plan-Driven methodology include:

- Predictability and Control
Detailed upfront planning establishes a clear project roadmap, enabling accurate estimation of resources, scheduling of milestones, and effective progress control. This is essential given the complexity of real-time synchronization and media communication and the limited size of the development team.

- Sequential and Phased Development
The project is decomposed into distinct phases—planning, design, development, testing, and integration—executed incrementally. Each major system component (e.g., realtime presence service, spatial audio/video service, workspace management module) is fully developed and validated before integration, reducing technical and integration risks.

- Comprehensive Documentation
Extensive documentation, including architectural specifications, design documents, and test plans, ensures traceability from requirements to implementation. This level of documentation supports academic evaluation, technical reviews, and future system maintenance.

- Stakeholder Alignment
Regular reviews conducted at the end of each increment allow stakeholders to evaluate progress, validate deliverables, and provide feedback within a controlled change management process, minimizing uncontrolled scope changes.

- Risk Mitigation
Early identification and documentation of risks related to realtime synchronization, audio/video stability, and scalability enable proactive mitigation, preventing major technical issues during later development phases.

Plan-Driven Implementation in the Virtual Workspace Project

To effectively apply the Plan-Driven methodology, the project follows a structured implementation approach based on incremental development.

1. Phased Development Process

The project progresses through the following phases:

- Planning Phase
Activities include detailed requirement analysis, system architecture definition, risk identification, and project scheduling. Core artifacts such as the Project Plan, ConOps, SRS, and initial architecture design are produced during this phase.

- Development Phase
The system is developed through a sequence of functional increments:

  - Increment 1: Core Realtime Infrastructure
Design and implementation of backend services supporting user sessions, presence synchronization, and basic realtime communication.

  - Increment 2: Spatial Interaction and Audio/Video Services
Implementation of proximity-based interaction logic and integration of spatial audio/video communication mechanisms.

  - Increment 3: Virtual Workspace and User Interface
Development of the 2D virtual environment, avatar movement, workspace layout, and user interaction interfaces.

- Optimization and Stabilization Phase
Performance optimization, system hardening, comprehensive testing, and final deployment of the MVP. This phase ensures system stability, acceptable latency, and compliance with defined quality criteria.

Each phase is governed by a clearly defined Definition of Done, requiring the completion of implementation, testing, documentation, and stakeholder approval.

2. Scheduled Reviews and Meetings

To ensure continuous monitoring and stakeholder alignment, the following review mechanisms are applied:

- Weekly Progress Meetings
Conducted to review completed tasks, upcoming activities, technical issues, and risks, ensuring adherence to the project plan.

- Increment Review Meetings
Held at the end of each increment to demonstrate implemented features, collect stakeholder feedback, and approve progression to the next increment.

- Final Review Meeting
Conducted during the optimization phase to evaluate the MVP, review system performance, and confirm deployment readiness.

- Increment Review Meetings: Conducted at the end of each increment (February 28, March 31, April 30) to demonstrate deliverables (e.g., working API Gateway, Data Service integration) to stakeholders, gather feedback, and approve the next phase.

- Optimization Review Meeting: Held on May 28 to present the MVP, review performance metrics, and finalize deployment approval.

3. Continuous Integration and Testing

Quality assurance is integrated throughout the development lifecycle:

- Continuous Integration (CI) pipelines are used to merge and validate code changes regularly, reducing integration conflicts.

- Automated and manual testing activities are performed at the end of each increment to verify functional correctness, realtime behavior, and audio/video stability

.

4. Stakeholder Collaboration and Feedback

Stakeholder engagement is structured and controlled. Feedback is collected during scheduled review sessions and incorporated through a formal change request process to maintain scope and schedule stability.

5. Plan-Driven Tools and Technology

The following tools support the Plan-Driven workflow:

- Project Management Tools: Jira or equivalent tools for task tracking and progress monitoring.

- Version Control Systems: GitHub and Git for collaborative development and configuration management.

Benefits of the Plan-Driven Approach

By applying the Plan-Driven methodology, the project expects to achieve:

- Predictable Delivery – A structured plan ensures timely delivery of the MVP within the defined schedule.

- Improved Quality – Systematic testing and documentation enhance system reliability and maintainability.

- Transparency – Regular reviews provide clear visibility into project progress and resource usage.

- Efficient Resource Utilization – Well-defined tasks and responsibilities improve team efficiency.

- Stakeholder Confidence – Controlled feedback and comprehensive documentation ensure alignment with stakeholder expectations.

The virtual workspace project leverages the Plan-Driven methodology to manage the complexity of real-time and interactive system development. Through a phased, incremental, and well-documented approach, the project aims to deliver a high-quality MVP while maintaining control over scope, risks, and quality within the given constraints.

## 2. PROJECT DEVELOPMENT PHASES/ITERATION

| No | Phase | Increment | Duration | Key Activities |
| --- | --- | --- | --- | --- |
| 1 | Project Planning & Research | Increment 1 | 2 weeks | - Define project scope, objectives, and success metrics - Research virtual workspace platforms and realtime technologies - Assign team roles and responsibilities - Set up repositories, CI/CD, and collaboration tools |
| 2 | System Design & Architecture | Increment 2 | 2 weeks | - Define system architecture (Frontend, Backend, Realtime, Media) - Design database schema and API contracts - Create UI/UX wireframes and interaction flows - Finalize incremental development plan |
| 3 | Core Backend & Realtime Development | Increment 3 | 3 weeks | - Implement backend services and authentication - Develop realtime presence and session management - Test APIs and realtime communication - Deploy initial backend infrastructure |
| 4 | Council Report Submission | Report | 2 weeks | - Prepare academic documentation - Present system design and architecture to the council |
| 5 | Spatial Interaction & Audio/Video Development | Increment 4 | 3 weeks | - Implement proximity-based interaction logic - Integrate spatial audio/video communication (WebRTC) - Test media connection stability and latency |
| 6 | Virtual Workspace UI Development | Increment 5 | 4 weeks | - Develop 2D virtual space and avatar movement - Implement workspace navigation and interaction UI - Integrate frontend with backend and realtime services |
| 7 | Feature Completion | Increment 6 | 4 weeks | - Implement chat and meeting modes - Implement workspace management features - Integrate access control and user roles |
| 8 | System Testing & Stabilization | Increment 7 | 3 weeks | - End-to-end system testing - Realtime and audio/video performance testing - Bug fixing and usability improvements |
| 9 | Council Counter-Argument. | Counter-Argument | 1 week | - Address council feedback - Justify design and architectural decisions |
| 10 | Deployment & Final Review | Increment 8 | 2 weeks. | - Deploy system to cloud environment - Finalize documentation and reports - Prepare release candidate |
| 11 | Council Final Defense | Defense | 1 week | - Present final system and project outcomes |

TABLE 7: PROJECT DEVELOPMENT PHASES\ITERATION

3.3 DETAILED SCHEDULE

| Phase | Task name | Duration | Start | End | Resource Name |
| --- | --- | --- | --- | --- | --- |
| Virtual Workspace Project |  | 136 days | 01/12/2025 | 4/5/2026 |  |
| Project Planning & Research | Define scope, objectives, success metrics | 3 days | 1/12/2025 | 4/12/2025 | Entire Team |
|  | Research virtual workspace & realtime tech | 5 days | 4/12/2025 | 9/12/2025 | Entire Team |
|  | Assign roles and responsibilities | 2 days | 10/12/2025 | 12/12/2025 | PM (Loc) |
|  | Set up repositories, CI/CD, collaboration tools | 4 days | 13/12/2025 | 17/12/2025 | Entire Team |
|  | Finalize project plan & timeline | 3 days | 18/12/2025 | 21/12/2025 | PM, SA |
| System Design & Architecture | Define overall system architecture | 5 days | 22/12/2025 | 27/12/2025 | SA |
|  | Design database schema & APIs | 5 days | 28/12/2025 | 2/01/2026 | SA,BE |
|  | UI/UX wireframes & interaction flows | 4 days | 3/01/2026 | 7/01/2026 | UX |
|  | Architecture and design review | 2 days | 8/01/2026 | 10/01/2026 | Entire Team |
| Core Backend & Realtime Development | Setup backend framework & services | 5 days | 11/01/2026 | 16/01/2026 | BE |
|  | Implement authentication & session logic | 7 days | 17/01/2026 | 24/01/2026 | BE |
|  | Develop realtime presence services | 10 days | 25/02/2026 | 05/02/2026 | BE |
|  | API testing & stabilization | 7 days | 06/02/2026 | 13/02/2026 | BE,QA |
| Spatial Interaction & Audio/Video Development | Implement proximity interaction logic | 7 days | 13/01/2026. | 20/01/2026 | BE |
|  | Integrate spatial audio/video (WebRTC) | 10 days | 21/01/2026 | 31/01/2026 | AV |
|  | Media performance testing | 7 days | 1/02/2026 | 08/02/2026 | AV,QA |
| Virtual Workspace UI Development | Develop 2D workspace & avatar movement | 14 days | 09/02/2026 | 23/02/2026 | FE |
|  | Implement UI navigation & interactions | 10 days | 23/02/2026 | 05/03/2026 | FE |
|  | Frontend integration with backend & realtime | 10 days | 05/03/2026 | 15/03/2026 | FE,BE |
| Feature Completion | Implement chat & meeting features | 7 days | 16/03/2026 | 23/03/2026 | FE,BE |
|  | Workspace management & permissions | 7 days | 24/03/2026 | 31/03/2026 | BE |
|  | Feature integration testing | 6 days | 01/04/2026 | 07/04/2026 | QA |
| System Testing, Deployment & Defense | System-wide testing & optimization | 7 days | 08/04/2026 | 15/04/2026 | Entire Team |
|  | Deployment & final documentation | 5 days | 16/04/2026 | 21/04/2026 | Entire Team |
|  | Council Final Defense | 7 days | 22/04/2026 | 29/04/2026 | Entire team |

TABLE 8: PROJECT DETAILED SCHEDULE

# IV. PROJECT RISK MANAGEMENT PLAN

## 1. RISK SOURCE AND CATEGORY

### 1.1 Risk Source

| No. | Source of risk | Description |
| --- | --- | --- |
|  | Requirement | Risks due to unstable, incomplete, or unclear user requirements related to realtime interaction, spatial audio/video behavior, or workspace functionality. |
|  | Design | Risks in translating requirements into a scalable and reliable virtual workspace architecture (e.g., realtime synchronization design, media pipeline design). |
|  | Code & Unit Test | Risks arising from defects in frontend, backend, realtime, or audio/video components during implementation and unit testing.. |
|  | Integration & Test | Risks in integrating frontend, backend, realtime services, and audio/video communication (e.g., synchronization issues, end-to-end latency). |
|  | Engineering Specialties | Risks related to specialized technologies such as WebRTC, realtime messaging, and browser-based rendering. |
|  | Development Process | Risks associated with executing the plan-driven methodology with controlled iteration (e.g., delays in increments, documentation gaps). |
|  | Development System | Risks from development tools, frameworks, and environments (e.g., CI/CD instability, browser compatibility issues). |
|  | Management Process | Risks related to project monitoring, milestone tracking, and coordination among team members. |
|  | Management Methods | Risks arising from quality assurance practices, workload distribution, and decision-making effectiveness.. |
|  | Resources | Risks due to limited time, team capacity, or infrastructure budget (e.g., team overload, cloud service costs). |
|  | Program Interfaces | Risks related to external stakeholders and interfaces (e.g., delayed mentor feedback, changing evaluation criteria). |
|  | External Services and Media Infrastructure | Risks associated with third-party services used for realtime communication and media delivery (e.g., TURN servers, cloud service availability). |

TABLE 9: LIST OF RISK SOURCE THAT ARE APPLICABLE TO THE PROJECT

### 1.2 Risk Categories

| No. | Risk Category | Description |
| --- | --- | --- |
| 1 | Technical risks | Risks related to the technology stack, realtime synchronization, audio/video communication, scalability, and browser compatibility. |
| 2 | Resource risks | Risks arising from constraints in personnel availability, time, or budget. |
| 3 | Process risks | Risks related to adherence to the selected plan-driven methodology, including documentation completeness and schedule compliance. |
| 4 | External Dependency risks | Risks arising from reliance on external platforms or services (e.g., cloud hosting, media servers). |
| 5 | Stakeholder Risks | Risks related to stakeholder expectations, feedback delays, or approval dependencies. |
| 6 | Others | Unforeseen risks not covered by the above categories, such as service outages or environmental disruptions. |

TABLE 10: LIST OF RISK CATEGORY THAT ARE USED BY THE PROJECT FOR ORGANIZING RISKS

## 2. RISK MANAGEMENT APPROACH

The approach to risk management in the virtual workspace project is proactive and iterative, aligned with the Plan-Driven methodology with controlled iteration. Given the complexity of realtime synchronization and spatial audio/video communication, risks are identified early, continuously monitored, and addressed systematically throughout the project lifecycle.

The following risk response strategies are applied:

- Avoid
Eliminate risks by selecting stable and well-supported technologies (e.g., choosing mature realtime communication frameworks and widely supported WebRTC implementations to reduce compatibility issues).

- Transfer
Shift certain risks to external services where appropriate (e.g., relying on managed cloud infrastructure or third-party media services to reduce operational and scalability risks).

- Control (Mitigate)
Reduce risk likelihood and impact through proactive actions, such as early prototyping of realtime synchronization and audio/video communication to identify integration issues at an early stage.

- Monitor
Continuously track identified risks and reassess their probability and impact during each project increment, especially risks related to schedule slippage, performance degradation, or system instability.

- Acknowledge (Accept)
Accept low-probability or low-impact risks without immediate action, such as minor UI inconsistencies or non-critical usability issues that can be addressed in later iterations.

## 3. TOOLS AND TECHNIQUE

To support effective risk management, the project employs the following tools and techniques:

- Risk Identification Workshops
Structured team discussions conducted during the early planning phase and at the start of major increments to identify potential technical, process, and resource risks.

- Risk Register
A centralized risk register maintained using project management tools (e.g., Jira), capturing Risk ID, description, category, probability, impact, mitigation strategy, owner, and current status.

- Probability–Impact Matrix
A qualitative matrix (Low / Medium / High) used to prioritize risks and determine appropriate response strategies during periodic risk reviews.

- Progress and Burndown Tracking
Monitoring task progress and completion trends to identify early indicators of schedule or resource risks.

- Early Technical Prototyping
Prototyping of critical components such as realtime presence synchronization and spatial audio/video communication to validate design assumptions and reduce integration uncertainty.

- Retrospectives and Review Sessions
Regular post-iteration reviews to evaluate realized risks, identify new risks, and refine mitigation strategies based on lessons learned.

## 4. RISK ITEM TO BE MANAGED

| Risk ID | Description | Source | Category | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Realtime synchronization instability (presence, movement lag) | Integration & Test | Technical | High | High | Early prototyping of realtime services; load testing; optimize message frequency and state updates | BE |
| R02 | Unclear or evolving requirements for spatial interaction and workspace behavior | Requirement | Technical | Medium | High | Iterative requirement validation through reviews; controlled SRS updates with stakeholder feedback | PM |
| R03 | Audio/Video connection instability or quality degradation. | Engineering Specialties | Technical | High | High | Early WebRTC prototyping; fallback connection strategies; continuous media performance testing | AV |
| R04 | Latency issues affecting proximity-based audio/video experience | Design | Technical | Medium | High | Optimize signaling flow; introduce latency monitoring; tune proximity thresholds | BE,AV |
| R05 | Overlapping roles leading to team overload | Resources | Resource | High | Medium | Reprioritize tasks; redistribute workload during weekly reviews; enforce clear ownership | PM |
| R06 | Schedule slippage due to underestimated realtime and media complexity | Management Process | Process | High | High | Add schedule buffer; freeze scope per increment; reprioritize non-critical features | PM |
| R07 | Limited experience with realtime or WebRTC technologies. | Development System | Technical | Medium | Medium | Knowledge sharing sessions; pair programming; use stable libraries and reference implementations | BE,AV |
| R08 | Cost overruns for cloud or media infrastructure | Resources | Resources | Low | High | Define infrastructure budget cap; monitor usage; evaluate managed service alternatives | PM |
| R09 | Integration issues between frontend, backend, realtime, and media services | Integration & Test | Technical | Medium | High | Early integration testing; use mock services; continuous integration and automated tests | SA,BE |

TABLE 11: RISK ITEMS TO BE MANAGED

## 5. RISK MONITORING AND CONTROL

- Weekly Monitoring: The Project Manager reviews the Risk Register on a weekly basis during progress meetings, updating probability and impact levels as project conditions change.

- Thresholds: Escalation is triggered if:

  - Increment delays exceed two working days (e.g., R06).

  - Realtime or audio/video integration tests fail more than 50% of executions (e.g., R01, R03).

- Mitigation Actions: Immediate mitigation actions are required for risks classified as High Probability / High Impact, such as prioritizing stabilization work or reallocating resources.

- Periodic Reassessment: Controlled risks are reassessed during increment review meetings to verify the effectiveness of mitigation strategies and adjust plans if necessary.

- Issue Tracking and Lessons Learned: Risks that materialize into actual issues (e.g., R09—service integration defects) are transferred to an Issue Log, where resolution actions and lessons learned are documented for future reference.

# V. PROJECT STAKEHOLDERS INVOLVEMENT

The GreenSprout project will involve stakeholders as follow:

| Role | Name | Description |
| --- | --- | --- |
| Mentor | Lecturer Nguyen Thi Thanh | The mentor of development team in Capstone Project |
| Development Team | Nguyen Quang Tri Huynh Cong Tan Nguyen Trung Hau Do Van Duong Chau Gia Kien Nguyen Toan Thang | The development team of Capstone project and responsible for develop GreenSpourt product. |

TABLE 12: PROJECT STAKEHOLDER INVOLVEMENT

# VI. PROJECT COMMUNICATION PLAN

## 1. KEY CONTACTS LIST

| No. | Name | Represent for | Contact Info | Interface |
| --- | --- | --- | --- | --- |
|  | Lecturer Nguyen Thi Thanh | Van Lang University |  | Mentor |
|  | Nguyen Quang Tri | Development Team | tri.2174801030001 @vanglanguni.vn | Project Manager, IoT Developer |
|  | Huynh Cong Tan | Development Team | tan.2174801030043 @vanlanguni.vn | IoT Developer |
|  | Nguyen Trung Hau | Development Team | hau.2174801030041 @vanlanguni.vn | Backend Mobile Developer |
|  | Do Van Duong | Development Team | duong.2174801030004 @vanlanguni.vn | Software Designer Mobile Developer |
|  | Chau Gia Kien | Development Team | kien.2174801030161 @vanlanguni.vn | Backend Web Developer |
|  | Nguyen Toan Thang | Development Team | thang.2174801030160 @vanlanguni.vn | Software Designer Web Developer |

TABLE 13 PROJECT KEY CONTACTS LIST

## 2. COMMUNICATION METHODOLOGY

| Audience/ Attendees | Topic/ Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| Mentor Development Team | Progress Review | 2 times/week | In-person |
| Development Team | Increment Progress | Weekly | 15-min Stand-Up |

TABLE 14 COMMUNICATION METHODOLOGY

----------- End of Document -----------